## EX - Sprint Planning Template
SPRINT PLANNING TEMPLATE |  |  |  | https://www.smartsheet.com/try-it?trp=11596&utm_source=integrated-content&utm_campaign=/content/sprint-planning-templates&utm_medium=Sprint+Planning+google+sheets+11596&lpa=Sprint+Planning+google+sheets+11596&lx=PFpZZjisDNTS-Ddigi3MyABAgeTPLDIL8TQRu558b7w
PROJECT NAME |  |  | ASL |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
Product Release |  |  | Alex B. |  | 2025-06-02 | 2025-07-25 | 35% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 |  |  |  | 2025-06-02 | 2025-06-15 | 14
Yes | Feature 1 | Project Planning & Setup | Team | 2 | 2025-06-02 | 2025-06-06 | 5 | Complete | High
No | Feature 2 | Research on Tech Stack (Mediapipe,T5) | John Lloyd | 3 | 2025-06-04 | 2025-06-10 | 7 | In Progress | Medium
| Feature 3 | Hand Detection (MediaPipe,OpenCV) | Jesse Rey | 5 | 2025-06-11 | 2025-06-13 | 3 | Not Started | Low
| SPRINT 2 |  |  |  | 2025-06-16 | 2025-06-28 | 13
| Feature 1 | Collect & Label ASL Gestures | Jericho | 6 | 2025-06-16 | 2025-06-20 | 5 | Overdue
| Feature 2 | Train Gesture Classifier Model (CNN/LSTM) | John Christopher | 6 | 2025-06-23 | 2025-06-27 | 5 | Needs Review
| Feature 3 | Evaluate Model Accuracy | Jesse Rey | 3 | 2025-06-27 | 2025-06-27 | 1 | Approved
| SPRINT 3 |  |  |  | 2025-06-30 | 2025-07-03 | 4
| Feature 1 | Integrate T5 Transformer (Hugging Face) | John Paul | 5 | 2025-06-30 | 2025-07-03 | 4 | On Hold
| Feature 2 | Chunking, Punctuation, Formatting | John Lloyd | 4 | 2025-07-04 | 2025-07-07 | 4
| Feature 3 | Combine Gesture Output with Sentence | John Christopher | 3 | 2025-06-10 | 2025-06-10 | 1
| SPRINT 4 |  |  |  |  | 2025-06-10
| Feature 1 | Evaluate Full System (Real-Time Test) | Team | 4 | 2025-06-10 | 2025-06-10 | 1
| Feature 2 | Write Final Paper | John Paul | 5 | 2025-07-18 | 2025-06-10 | -37
| Feature 3 | Oral Presentation Preparation | Team | 5 | 2025-06-10 | 2025-06-10 | 1
| SPRINT 5 |  | Frank C.
| Feature 1 |  | Shari W.
| Feature 2 |  | Shari W.
| Feature 3 |  | Kennedy K.
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Sprint Planning
SPRINT PLANNING TEMPLATE
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
|  |  | Jesse Rey Isidro |  | 2025-06-02 | 2025-07-25 | 0% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 |  | John Lloyd
No | Project Planning & Setup | Setup | Team | 2 | 2025-06-02 | 2025-06-06 | 5 | Complete | Low | Repo, tools, folder structure
No | Research on Tech Stack (Mediapipe,T5) | Research | John Lloyd | 3 | 2025-06-04 | 2025-06-10 | 7 | Complete | Low | Confirm tools and API support
Yes | Hand Detection (MediaPipe,OpenCV) | Development | Jesse Rey | 5 | 2025-06-11 | 2025-06-13 | 3 | In Progress | High | Real-time detection
| SPRINT 2 |  | Jesse Rey
| Collect & Label ASL Gestures | Data Collection | Jericho | 6 | 2025-06-16 | 2025-06-20 | 5
| Train Gesture Classifier Model (CNN/LSTM) | Model Training | John Christopher | 6 | 2025-06-23 | 2025-06-27 | 5
| Evaluate Model Accuracy | Testing | Jesse Rey | 3 | 2025-06-27 | 2025-06-27 | 1
| SPRINT 3 |  | Jericho
| Integrate T5 Transformer (Hugging Face) | NLP Integeration | John Paul | 5 | 2025-06-30 | 2025-07-03 | 4
| Chunking, Punctuation, Formatting | NLP Formatting | John Lloyd | 4 | 2025-07-04 | 2025-07-07 | 4
| Combine Gesture Output with Sentence | Pipeline Integration | John Christopher | 3 | 2025-07-08 | 2025-07-11 | 4
| SPRINT 4 |  | Team
| Evaluate Full System (Real-Time Test) | System Training | Team | 4 | 2025-07-14 | 2025-07-17 | 4
| Write Final Paper | Documentation | John Paul | 5 | 2025-07-18 | 2025-07-22 | 5
| Oral Presentation Preparation | Presentation | Team | 5 | 2025-07-23 | 2025-07-25 | 3
SPRINT 5
Feature 1
Feature 2
Feature 3
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.